## Sheet1
Task | Hours of Effort | Hourly Rate | Cost
Initiation
Identify High-level Requirements | 4 | 100 | 400
Identify Personas | 4 | 100 | 400
Identify Detailed Requirements | 4 | 100 | 400
Planning Planning (Frontend and Backend)
Software Requirements Specification | 8 | 100 | 800
Software Design Document
High-level Wireframe (Main screens and relationships) | 10 | 100 | 1000
Detailed list of screens with contents | 10 | 100 | 1000
Use-case diagram | 6 | 100 | 600
List of Use Cases: 1 Successful & 1 Alternate Scenario each | 10 | 100 | 1000
Project Management Plan
Scope Statement | 12 | 100 | 1200
Work Breakdown Structure and Activities | 12 | 100 | 1200
Schedule | 15 | 100 | 1500
Budget | 12 | 100 | 1200
Risk Breakdown Structure and Matrix | 12 | 100 | 1200
Risk Probability/Impact Matrix | 12 | 100 | 1200
Prototype Development (User-facing)
Create Home screen | 10 | 75 | 750
Develop Menu Bar, Header, and Footer Elements | 8 | 75 | 600
Create Services screen(s) | 15 | 75 | 1125
Create Login screen(s) | 10 | 75 | 750
Create Donation screen(s) | 8 | 75 | 600
Create Volunteer screen(s) | 8 | 75 | 600
Create Events screen(s) | 15 | 75 | 1125
Handoff & Post-mortem
Finalize and submit source code, screenshots and documents | 10 | 100 | 1000
Create Project post-mortem document | 4 | 100 | 400
Hardware Costs (asset purchases or cloud useage costs)
Backup storage fordatabases and site information |  |  | 200
Hosting (Annually) |  |  | 500
SSL certificate (Annually) |  |  | 150
Domain (Annually) |  |  | 15
Fees for COTS
N/A (Site is self-contained. Card processing for event fees not considered) |  |  | 0
Fees for tools
N/A (all development software is freely available) |  |  | 0
Total Project Cost |  |  | 20915