## Sheet1
Risk Register
Risk | Description
overwhelming use | Higher than expected use leaves BCS unable to keep up
change in org structure | BCS services / process is altered from requirements page
Scope Definition | Scope misjudgment leads to missing requirements
miscommunication of needs | Project description failed to communicate a need that was not identified and incorporated in design
unforseen regulations | Unknown government requirements could result in deficiencies in design and implementation
security / privacy | Oversight of vulnerabilities could lead to compromised site security
race condition between users | Not properly handling an event where multiple staff are interacting with a calendar or other shared resource could result in overlapping commitments or unexpected data.
budget | Budget estimates fail to match the required work
schedule | Time required to complete tasks is off from estimates, causing delays or reduction in quality or scope of product
personas | users of the software misinterpreted or incomplete
missing reqs | Analysis of project description and/or oversight in communication by BCS leads to missing requirements that leave the product unsatisfactory
site flow issues | Sitemap design is difficult to understand by users, leading to a poor product
missing use cases | Essence of the system not captured by use cases in terms of accuracy and/or completeness.
difficult to use | Design decisions make product awkward or difficult for staff/public to use
unforseen risks
design difficulty | Elements of the layout or features included in the design are more difficult to implement than expected.
hosting / database miscalc | The level of hosting and data storage is inappropriate for the customer's needs.
hardware failure | Development hardware fails or is inadequate for the creation of the product.
prioritization failure | Priority of tasks is misjudged, leading to missing or underdeveloped key features compared to less important ones.
unexpected needs assumed | Needs unanticipated by BCS are identified and added to the project scope, requiring time and resources, but delivering a stronger and more accurate product.
staff needs more access | The design of the site gives insufficient acces to staff or the public.
reliability | The code or services fail to provide consistent service in a product upon which health and safety are concerned (external services in particular).