## Sheet1
Risk Register
# | Risk | Description
1 | Scalability | Failure to develop a system that can adapt to higher than expected use could leave BCS unable to operate as needed.
2 | Changes to BCS organizational structure | Alterations in BCS services / process from the given requirements could cause critical usability issues.
3 | Scope definition | Poor analysis of project description leads to missing requirements and a final product that does not capture the essence of the desired software.
4 | Miscommunication of needs | Project description failed to communicate a need that goes unidentified and is not incorporated in design.
5 | Unforseen regulations | Unknown government requirements could result in deficiencies in design and implementation, potentially causing rework, a break in service, or punitive measures.
6 | Security / privacy issues | Oversight of vulnerabilities could lead to compromised site security.
7 | Race conditions | Not properly handling potential simultaneous use of shared resources could result in overlapping commitments or corrupted data.
8 | Budgetting | Budget estimates fail to match the required work, requiring either a request for more funding, an incomplete product, or a lower return on investment.
9 | Scheduling | Time required to complete tasks is off from estimates, causing delays or reduction in quality or scope of the product.
10 | Personas | Users of the software misinterpreted or incomplete, possibly leading to the design and implementation meeting the wrong needs.
11 | Difficult to use | Design decisions make product awkward or difficult for staff/public to use in some cases.
12 | GUI implementation | Elements of the layout or features included in the design are more difficult to implement than expected.
13 | Hosting / Database miscalculation | The level of hosting and data storage is inappropriate for the customer's needs.
14 | Hardware failure | Development hardware fails or is inadequate for the creation of the product.
15 | Poor prioritization | Priority of tasks is misjudged, leading to missing or underdeveloped key features compared to less important ones.
16 | Unexpected needs | Needs unanticipated by BCS are identified and added to the project scope, requiring time and resources, but delivering a stronger and more accurate product.
17 | Insufficient access | Due to a lack of access: BCS staff is unable to perform needed work / Customers are unable to access needed features of the organization.
18 | Unintended access | Design flaws allow BCS staff or customers to access unnecessary components of the product.
19 | Reliability Issues | The code or services fail to provide consistent service in a product upon which health and safety are concerned (external services in particular).
20 | Inflexible design / implementation | Without a sufficiently flexible design and implementation, needed changes could require a lot of avoidable work.
21 | Technology Viability | The development tools chosen do not meet project needs, requiring extra work within the system or adoption of different tools.
22 | Funding | BCS struggles to pay for development services in part or full.